## Schedules
| Job Name | Address | Pool (P) or Pool Spa (PS) | Permit Number | Field Manager | Permit Application | Permit Received | Excavation | Form & Steel | Quality Inspection (QI) 1 | Gunite | QI 2 | Survey | Backfill | Plumbing | QI 3 | PSI. Inspection | Coping | Tile | QI4 | Rail Anchors | Bonding Grid Inspection | Deck Inspection(s) | Footer/Sub-Deck | Paver Installation | QI 5 | Elec. Sub-Panel | Equipment Installation | Equipment Wiring | QI 6 | Screen/Fence | Electric Inspection | Safety Inspection | Plaster | Startup | Final QI | Final Inspection (s)
1 | Guflstream - Nani | 4406 Crayton Rd., Naples | PS | PRPO2400132 |  | 2024-01-01 | 2024-03-20 | [5 empty] | 2025-01-13 |  |  |  | 2025-01-24 |  |  |  |  | 2025-07-01
2 | Gulfstream - Graeve | 5925 Bur Oaks Ln., Naples | PS | PRSPL20250523567 |  | 2025-05-30 | 2025-07-10 | [9 empty] | 2025-10-24 |  |  |  |  | 2026-01-16 |  | 2026-01-28
3 | Gulfstream - Korchmar | 116 Heron Ave., Naples | PS | PRSPL20251043963 |  | 2025-10-16
4 | Gulfstream - Glance | 5718 Green Blvd., Naples | PS | PRSPL20260205002 | Reilly/Matt | 2026-02-06 | 2026-03-20 | 2026-04-21 |  |  | Q.I. 04/22
5 | Gulfstream - German Woods | 3241 German Woods Ct., Naples | PS | PRSPL20260207499 | Mike/Matt | 2026-02-24 | 2026-03-27
6 | Gulfstream - Lolli | 6587 Bottlebrush Ln, Naples | PS | PRSPL20260311105 | Mark/Mark | 2026-03-18 | 2026-04-17
7 | Gulfstream - Stevens | 5111 Palmetto Woods Dr., Naples | PS | PRSPL20260311153 | Kevin/Matt | 2026-03-18 | 2026-04-21
8 | Gulfstream - Dean | 6988 Hunters Rd., Naples | PS | PRSPL20260313172 | Mark/Mark | 2026-03-31 | Environmental 04/06 - Plumbing 04/07 - Zoning xx/xx - Engineering xx/xx
9 | Gulfstream - Regelbrugge | 504 97th Ave N., Naples | PS | PRSPL20260413590 | Ian/Joe | 2026-04-02 | ORIG. SIGNOFF 02/2/26 - WAITING REVISED SIGNOFF AS OF 03/31 - Environmental xx/xx - Plumbing xx/xx - Zoning xx/xx - Engineering xx/xx - PLMB/HANDI REJECTED 04/20. NEED FEATURE AND RAIL ADDON DETAILS
10 | Gulfstream - Illinois Dr | 1038 Illinois Dr., Naples | PS | PRSPL20260415539 | Mike/David | 2026-04-14 | Environmental xx/xx - Plumbing xx/xx - Zoning xx/xx - Engineering xx/xx
11 | Baker - Aarts | 2202 NW 8th PL, Cape Coral | P | WEB21-34528 | Tony | NEEDS PERMIT FINALLED/CLOSED
12 | Baker Const - Munster | 2811 SW 25th ST., Cape Coral | PS | WEB22-03415 | Tony | NEEDS PERMIT FINALLED/CLOSED
13 | LaGrasta - 509 92nd | 509 92nd Ave N, Naples | PS | PRSPL20250311840 | Nick | 2025-03-20 | 2025-04-30 | [9 empty] | 2025-08-20 |  |  |  |  | 2025-08-20 |  | 2025-10-17 | [10 empty] | 2026-04-14
14 | Ricardo | 4208 33rd ST SW, Lehigh | PS | POL2024-00145 | Ricardo
15 | AB Homes - Wantoch | 335 Burning Tree Dr., Naples | PS | PRSPL20250837184 | Max | 2025-08-28 | 2026-01-05 | [9 empty] | 2026-03-27
16 | AB Homes - Longboat | 2281 Longboat Dr., Naples | PS | PRSPL20260207519 | Max | 2026-02-24 | Plumbing 03/12 - Zoning REJECTED 03/26 - REJECTED Engineering 03/26 - WAITING DESIGN REVISION APPROVAL AS OF 03/31
17 | Kingdom Builder - Gargano | 3828 Crayton Rd., Naples | PS |  | Mark |  | SIGNOFF REC'D 01/30/26 - TDH DONE - WAITING ON SITE AND DRAINAGE PLANS AS OF 03/31
18 | LaGrasta - Genovesi 2 | 9940 Vanderbilt Dr., Naples | PS | PRSPL20260416972 | Nick | 2026-04-22 | Environmental xx/xx - Plumbing xx/xx - Zoning xx/xx - Engineering xx/xx